## Sheet1
MSD TaskList
S.No | Task | Progress | Progress Bar | Remarks
1 | Cumulative Table (up to current iteration )included in the loop with cumulative count and total number of particles | Done | 100%
2 | Aggregate Summary Table at end | Done | 100%
3 | Cumulative Histogram Table at end | Done | 100%
4 | Change “powder analysis” to X Routine Analysis in report where X = MG44 or MG45 | In Progress | 95% | Refer point 8 updated request on 26 Oct 2021
5 | Bigger Images in the report | Done | 100%
6 | Edit Report format Image 1 <result as per (a)> Image 2 <result as per (a)> Summary of Results (Cumulative) à This can be a header. <table that total up the counts from all the images captured> | Done | 100%
7 | Raw Data Files (to be shown under results section, whereby user can view and print directly) | Done | 100% | sk
8 | Total 4 job templates - MG44 (2 table formats), MG45 (2 table formats) | Done | 100% | Revised request on 26 Oct 2021
9 | Amend main form and footer form | Done | 100% | Revised request on 26 Oct 2021
10 | Validation Memo | In Progress | 100%
|  | Total progress | 100%

## Sheet2
MSD Requirement List
S.No | Task | Progress | Progress Bar | Remarks
1 | Cumulative Table (up to current iteration )included in the loop with cumulative count and total number of particles | Done | 100%
2 | Aggregate Summary Table at end | Done | 100%
3 | Bigger Images in the report | Done | 100%
4 | Edit Report format Image 1 <result as per (a)> Image 2 <result as per (a)> Summary of Results (Cumulative) à This can be a header. <table that total up the counts from all the images captured> | Done | 100%
5 | Raw Data Files (to be shown under results section, whereby user can view and print directly) | Done | 100% | Raw data can be viewed from Results. To print, need to export to a folder
6 | Total 4 job templates - MG44 (2 table formats), MG45 (2 table formats) | Done | 100% | Revised request on 26 Oct 2021
7 | Amend main form and footer form | Done | 100% | Revised request on 26 Oct 2021
8 | Validation Memo Draft | Done | 100%
9 | Cumulative Histogram Table at end | Done | 100%
10 | Change eye piece to objective | Done | 100% | Revised request on 29 Oct 2021
11 | Add workflow name to the report | Done | 100% | Revised request on 29 Oct 2021
12 | Make count display visible | Done | 100% | Revised request on 29 Oct 2021
13 | Add zero to the last but one column and dash to the last column | Done | 100% | Revised request on 29 Oct 2021
14 | Units of measure in report, namely the um in the table | Done | 100% | Revised request on 29 Oct 2021
|  | Total Progress | 100%